## Slide 1: Stormwater Master Plan

## Slide 2
Stormwater Master Planning
(status through 2/25/2019)
Chart: Cuyahoga River South
| Stormwater Master Plan | Alternatives Development | RSS Modeling | Condition Assessments | Field Investigations | Data Collection & Review
Complete | 0.988 | 1 | 1 | 1 | 1 | 1
Remaining | 0.012 | 0 | 0 | 0 | 0 | 0
Chart: Cuyahoga River North
| Stormwater Master Plan | Alternatives Development | RSS Modeling | Condition Assessments | Field Investigations | Data Collection & Review
Complete | 0.0764 | 0.5533 | 0.7784 | 1 | 1 | 1
Remaining | 0.9236 | 0.4467 | 0.2216 | 0 | 0 | 0
Chart: Rocky River
| Stormwater Master Plan | Alternatives Development | RSS Modeling | Condition Assessments | Field Investigations | Data Collection & Review
Complete | 0.1255 | 0.2824 | 0.6804 | 0.8709 | 0.8709 | 0.8709
Remaining | 0.8745 | 0.7176 | 0.3196 | 0.1291 | 0.1291 | 0.1291
Chart: Chagrin/Lake Erie
| Stormwater Master Plan | Alternatives Development | RSS Modeling | Condition Assessments | Field Investigations | Data Collection & Review
Complete | 0 | 0.1 | 0.04 | 0.1076 | 0.1076 | 0.1076
Remaining | 1 | 0.9 | 0.96 | 0.8924 | 0.8924 | 0.8924
Completion Date: April 2020
Completion Date: May 2021
Completion Date: April 2019
Completion Date: November 2019

## Slide 3: CRN Stormwater Master Plan Study Area
Total Study Area
99,000 acres (all within SWSA)
11 Subwatersheds in the SWSA
23 WAC Member Communities
Budget: $8.02 Million
Completion: November 2019

## Slide 4: Stormwater Master Plan Modeling & Problem Identification Project Status
Task Item Status: 77% Complete
Stickney Creek Complete
B.C. Main Branch Complete
B.C. West Branch Complete
West Creek Complete
Hemlock In Progress
Mill Creek In Progress
Combined Sewer Area
In Progress
Small Tributaries Not Started
Hemlock Creek

## Slide 5: Stormwater Master Plan Alternative Evaluation Project Status
Task Item Status: 55% Complete
Stickney Creek Complete
B.C. Main Branch Complete
B. C. West Branch Complete
West Creek Complete
Hemlock In Progress
Small Tributaries Not Started
Mill Creek Not Started
Combined Sewer Area Not Started

## Slide 6: Early Action Project
Brookside Blvd Culvert, Asset ID # WB0019

## Slide 7: Brookside Culvert
September 24, 2018 CCTV Photograph –
Close up view of deflection
May 12, 2017 CCTV Photograph
Close up view of Deflection
CCTV Inspection noted buckling in CMP
north wall & holes in top of culvert
Reference Corrosion Mark
Notes: Degree of buckling went from 5% to 20% per PACP criteria.
Initial inspection with CCTV in 2017. B&C in 2018 noticed additional buckling of pipe

## Slide 8: Brookside Blvd Culvert
August 17, 2018 Field Visit Observation~2in x 1/8 in holes forming on top of CMP

## Slide 9: Brookside Blvd Culvert
SWIM inspection – February 2019

## Slide 10: Brookside Blvd Culvert
SWIM inspection – February 2019

## Slide 11: Early Action Project
Brookside Blvd Culvert, Asset ID # WB0019
Exposed culvert
North wall buckling – 422 ft.
Ceiling holes – 440 – 452 ft.
Exposed culvert
North wall buckling – 470 - 479 ft.
Exposed culvert
Inverse curvature buckling – 510.5 ft.
Notified Cleveland and Coordinating on
Temporary and Long-term Fix

## Slide 12: Stormwater Master Plan Community Communication
Meet with communities
  Problem Area Review
Recommendations and Community Report – 4th Quarter 2019
Watershed Team Leaders serve as the point of contact between the communities and the District

## Slide 13
Questions